Mission:

We promote self-sufficiency and provide basic living expenses to Alaskans in need.

GOAL #1:  Self-sufficient individuals and families

| Strategies | FY06 Objectives | Steward | Status | Comments |
| --- | --- | --- | --- | --- |
| - Help low-income needy adults move into employment and support the development of stronger families. | - Continue Family Centered Service program and related integration efforts. - Implement CITC Native Family Assistance Program. - Plan for implementation of Native Family Assistance Programs with BBNA and Manillaq Association for delivery of culturally appropriate services. - Promote Healthy Marriages. - Develop and implement policies and strategies that reduce teen and out-of-wedlock pregnancy and prevent statutory rape. - Collaborate with Labor on the WIA reauthorization. | KF EF AS RK RK KF |  | 1. FCS project underway; partnership day is scheduled 10/05. Oct. 26, 2005 2. Project is operational. Grants approved. Working with CSSD. 3. BBNA has postponed start date to July 2006. Negotiating NFAP grant with BBNA; Manillaq in early planning stages, no date set. 4. Rec’d six proposals PEC scheduled for August 2005. 5. Action and spending plan targeted for September 2005. 6. Need to insure we are in plans Add link to integrated MOU. |
| - Provide ‘safety-net’ services and basic living expenses for Alaskans in need. | - Continue to deliver basic benefits* and quality services while adapting and contributing to changes as needed per legislative and administrative priorities. *Benefits include: Adult Public Assistance, Alaska Temporary Assistance Program, Child Care Assistance, Denali Kid Care, Food Stamps, General Assistance, Heating Assistance, Interim Assistance, Medicaid, Medicare Part D, Senior Care. - Implement Medicare Part D prescription option. Transition Senior Care Program. 3) Enhance outreach of multiple programs and continue to meet targets when needed. | KF AS MR |  | 1. See Performance Measures. Governor needs to sign the bill. 2. Work groups meeting regularly. New staff hired 9/05. Implementation is 01/06. 3. Will be responsive to FNS requests/requirements. Posters and mail outs in fall before program startup. |
| - Promote the employability of Alaskans with disabilities. | - Continue participation in the Customized Employment Grant (CEG). - Continue participation the Alaska Works Initiative grant. - Complete regulation changes to increase resource limits for working disabled Medicaid Buy-In Option. | AS AS AS |  | 1.Sustainability committee met 7/25/05. 2. Two position Anc/Fbks & Steering Committee participation. 3. Revised proposal with Commissioner’s Office for review. |

GOAL #2:  Effective & Efficient Service Delivery

| Strategies | FY06 Objectives | Steward | Status | Comments |
| --- | --- | --- | --- | --- |
| - Align services, policies, and programs to promote integrated customer / family-centered services. | - Integrate PASS I Services, regulations and policies into the Child Care Program Office structure. - Revise and implement program policies to promote integration, administrative efficiency, and employment outcomes. - Review and/or implement integration of CCL function into DPH Certification Licensing Unit. | ML EF ML |  | 1.Pass I regulations drafted and out for Public Comment and process and policy integration is in process - On Track; Refer to section plan. FCS activities. Development of Policy White Papers on Hoback Recommendations. Target October 2005. 3. Start review in FY06. |
| - Build regional, community and tribal partnerships that enhance integrated, community-based, services. | - Plan for transfer of Medicaid eligibility responsibility to Native TANF providers. - Increase enrollment of IHS patients eligible for Medicaid to Enhance Federal Financing of Benefits. (ANMC and YKHC). - Implement a statewide refugee assistance program in partnership with Catholic Social Services. - Continue develop of a tribal Food Stamps demonstration project with Tanana Chiefs Conference. - Work with Tribal CCDF grantees to improve the integration of Child Care services to Native families. - Implement the CC capacity in rural communities plan. - Strengthen regional coordination of services across DHSS. | AS MR RK AS ML ML KF |  | 1. Feasibility study; see Section plan. 2. We are planning start-up for mid/late-August. We plan on outstationing one of our existing workers at ANMC and post the vacancy to hire. MOU is on the way to Kitty for review. 3. FY06 Procurement done. Initial operational planning meeting done. Coordination meeting CSS August 2005. 4. Need to redefine scope and determine priority. 5. In Progress 6. Workload and staff resource issue. 7. Plan in development. Retreat held in July. Field technical assistance scheduled for fall. Regional council capacity building grant with Foraker Group done. |
| - Collaborate with Alaska Job Center Network partners to move from co-location to true integration of employment services. | - Participate in Job Center redesign projects at the five CEG sites (Juneau, Mat-Su, Kenai, Fairbanks, and Muldoon). - Maintain an active role in the operations & management of the Alaska Job Center Network. - Investigate options of Mat-Su collocation of licensing specialist and CC resource and Referral staff at job center. | MR MR ML |  | 1. Redesign is well underway with Muldoon beginning build out. Kenai, Wasilla, and Juneau have been remodeled. Fairbanks has proposed relocation. Triage, common orientation, job development will be topics discussed at our upcoming meeting. 2. Ongoing meetings with Directors, strengthening with AWIB. 3. DPA expanded space is secured. Collocation options are being explored. |
| - Leverage technology to enhance service provision and information sharing within the department and with partner agencies and to increase remote access/‘self-service’ features. | - Define the Division’s IT needs and priorities. Ensure IT has a plan project and work request priorities, including capital investments and a long-term technology strategy for EIS. - Complete strategy and begin implementation for a common Consumer Information / Master Client Index pilot, including parameters for information sharing and confidentiality. - Implement the AJCN web based common orientation tool in at least one site. - Implement ICCIS use statewide; incorporate Pass I; plan for system modifications and maintenance. - Implement enhanced online manuals. - Implement SSOL for SSA. | MN KF MR ML/PS EF PS |  | 1. Leadership Team met 7/26/05. Paul and Margo putting together project list with timeframes, resources, and funding sources. Paul going to 08/05 APHSA-ISM. 2. Strategy being redefined by MCI team. - Will be discussed at our upcoming meeting. 4. System is in test. Pilot Office includes Juneau, Kenai, Mat-Su and Valdez. Starts 8/15/05 Juneau. 5. 08/05 begins training Yvonne on Robo Help. 6. Off wait list; first meeting 5/17/05. Mary to follow up with Paul. |
| - Assess and adopt strategies that leverage statewide support units and call center. | - Complete a workload analysis to examine caseload trends, resourcing strategies and shifts (e.g. contracting), workload methods (Call Center), complexity, and increasing partnerships. | MR |  | 1. Project dates have shifted based on Scott’s presentation. Will be meeting with Margo to draft ASPS. We are looking at March and April to conduct ‘beeper’ work. |

GOAL #3:  Quality Workforce

| Strategies | FY06 Objectives | Steward | Status | Comments |
| --- | --- | --- | --- | --- |
| - Enhance employee recruitment, and retention to reduce the risk of turnover. | - Provide training to supervisors on writing PDs, HR hiring processes, effective evaluations, and exit interviews. - Define and implement HR database / tracking tool. | MR MN |  | 1. Work is still being done around evaluations and hiring. Suzi will be releasing a project that Central has done soon. 2. Tapestry Pilot implemented 7/1/05; proceeding with next steps, i.e. evaluation, 360, goals, & requirements. |
| - Expand cross-training and career development initiatives within DPA and with partner agencies. | - Conduct a series of Learning Summits to ~ 10 sites. - Expand the use of e-learning tools, e.g. electronic pre-packet and NetMeeting. - Establish coaching and mentoring program and ensure training. - Create a training internship program. | MCM MCM MCM MCM |  | 1. Start planning for FY06 Done. Will do AAR in August. 2. Nome and Bethel pilot – underway and in use. 3. Ongoing 4. Started scoping. |
| - Align and streamline job classifications to support an integrated client-centered model. This needs to be revised. | - Submit to the Department the ET and WDS series’ to DOP for reclassification study. - Contribute to DHSS evaluation and reclassifications of the Admin. Clerk series. | MR MR |  | 1. Will initiate revision of Minimum Qualification/Substitution. Plan is to include PAA series, too. 2. DHSS responded to DOP inquiry on 7/27/05 to include DPA for those admin clerks that are performing front desk duties in our storefront operations and meeting with the public on an extensive basis. |
| - Implement leadership development programs that mitigate the risks of turnover and promote a culture of teamwork. | - Define key leadership jobs & critical experience and competencies / minimum qualifications for each. - Pilot Personal Development Plans for the Extended Leadership Team members. - Identify and leverage personal development opportunities for staff, such as Summit, Peer Review and Hiring team participation. | MN MCM MCM |  | 1. Division Chiefs are to create Section/Unit strategies for positions needing knowledge transfer. ET, WDS, and PAA classes identified 7/26/05 for change in MQ. 2. Pilot of Tapestry from 6/05 to 12/05 3. Ongoing; diversifying hiring teams. |

GOAL #4:  Stewardship and Accountability

| Strategies | FY06 Objectives | Steward | Status | Comments |
| --- | --- | --- | --- | --- |
| - Enhance performance improvement and quality initiatives to meet or exceed the accuracy and timeliness of benefits. | 1) Sustain the Food Stamp accuracy campaign. 2) Develop improved accuracy measures for Medicaid and APA programs. 3) Develop and sustain contract site and contract compliance review process. Incorporate assessment methods to add Child Care contracts into the process. 4) Develop and implement PERM Quality Assessment process and supporting structure. 5) Improve capability to measure application processing and benefit issuance timeliness. 6) Maintain fraud control and benefit recovery practices, while increasing trend information sharing. | JD JD JD JD JD JD |  | 1. Ongoing updates with emphasis on campaign. Hanging in there, but not at target. 2. Involves special QA projects and sampling, APA pilot test underway. FY06 expand APA sampling methods. Implement PERM for Medicaid. 3. Pilot assessments this month with Child Care provider. 4. Still waiting release of final regulations end of 8/05 to determine impact on eligibility review requirements. 5. WR 5818; Project has three components. Cycle time done, timely issue under development; delay reason code recently assigned and active. 6. Claims/fraud info posted on webpage. PIA will compile FY05 annual claims recovery and establishment summary. Title: Fraud Control Unit Accomplishments Report. Target Post to DPAWeb 10/01/05. |
| - Establish integrated performance management processes that align individual, team and organizational goals with the mission of DPA. | 1) Complete the DPA Annual Performance Contract & Strategic Plan; annual Section plans; monitor progress monthly. 2) Develop Service Level Agreements and set priorities with FMS service providers: IT, Communications, Grants & Contracts, HR. | MN MN |  | 1. Ongoing 2. FMS is working on informal SLA for IT services. No activity with HR and Grants and Contracts. |
| - Identify and as appropriate, implement changes that help to contain programmatic and administrative cost of services. | 1) Evaluate FY06 financial management plans and development FY07 operating budget changes. 2) Plan and develop FY07 Capital budget. 3) TANF investment strategies. | RM MN KF |  | 1. Initiate in July 06 - Due to DHSS August 2005, due to OMB October 2005. 3. Ron K. is updating plan from our 7/26/05 meeting. |
| - Ensure continuous improvement efforts drive progress and key performance indicators. | 1) Continue effective and efficient delivery of Work Services. 2) Create an evaluation and feedback culture through self-assessments, Quality Councils, and effective monitoring. 3) Implement DHSS Fair Hearing process improvements. | RK CMC EF |  | 1. FY06 revise and enhance performance measurements by developing new payment points for FY07. FY06 reporting requirements to improve monitoring process. 2. Support QC implemented 6/05. KF facilitator; webpage’s updated; updated QC Flow diagram. AAR done 6/15/05. Next one is 9/28/05. 3. DHSS Workgroup is developing recommendations for process improvements. |
| - Reduce predictable risk and ensure the health and safety of children in childcare. | - License CC providers, implement quality improvement initiatives, and develop Early Learning Guidelines. | ML |  | 1. Early Learning Guidelines on hold until June. |
| - Ensure continuation of program funding by meeting federal program compliance standards | - Timely completion and submittal of program state plans, program waivers, and FS reinvestment plans. - Timely completion and submittal CC state plans. - Timely completion of corrective action plans. - Timely Completion and submittal of quarterly federal financial reports for Food Stamps, Medicaid, TANF, and CCDF. - Timely completion and submittal of the LIHEAP State plan. - EBT cash and food settlement and reconciliation. | EF ML JD RM MR MR |  | - Program State plans and waivers are on track for delivery 8/15/05.FS reinvestment Jim D. met with managers to develop plan and submitted the spending plan to Janet Clarke. Pending OMB approval. - CCDF Plan will be submitted by July, which will require modification prior to approval. - Submitted 5/2/05, next due 11/05; need to track how we handle transition with Val Horner leaving. - Ongoing. Deadlines fall quarterly. - Due in Aug/Sept 2005. - Ongoing. |